## Action list
Container_Task | task_id | start | Effort | allocate | BLOCKER | status | notes
Milestones | start project | 2014-02-22
Milestones | Mid-term review | 2014-04-08 |  |  | doing a lot |  | this is a review of phase3 outcomes and outputs
Milestones | end project | 2014-06-28 |  |  | completion
Phase1 | Test tj3 A |  | 1w | toA | start project | TODO
Phase1 | Test tj3 B |  | 1w | toB | previous-sibling | TODO
Phase2 | Test 2 tj3 |  | 2w | toA | Test tj3 B | TODO
Phase2 | Test 2 tj3 B |  | 2w | toB | previous-sibling | DONE
Phase3 | doing a lot |  | 1d | toC | Test 2 tj3 B | TODO
Phase3 | and more and more | 2014-05-01 | 3w | toA | doing a lot | TODO
Phase4 | finalising |  | 2d | toB | and more and more | TODO
Phase4 | completion |  | 2d | toA | finalising | TODO

## Resources
resource_id
toA
toB