## Action list
Container_Task | task_id | start | Effort | allocate | BLOCKER
Milestones | start project | 2014-02-22
Milestones | Mid-term review | 2014-06-28
Phase1 | Test tj3 A |  | 1w | toA
Phase1 | Test tj3 B |  | 1w | toB | previous-sibling
Phase2 | Test 2 tj3 |  | 2w | toA | Test tj3 B
Phase2 | Test 2 tj3 B |  | 2w | toB | previous-sibling
Phase3 | doing a lot |  | 1d | toC | Test tj3 A

## Resources
resource_id
toA
toB